PROJECT PLAN

DairyPro 360 — All-in-One Dairy Management System

Version 1.0  |  25 May 2026  |  7-Week Delivery Plan

| Document ID | PP-DMS-2025-001 |
| --- | --- |
| Version | 1.0 |
| Prepared By | Project Manager Agent (PMP-certified) |
| References | BRD-DMS-2025-001 v1.1 (Validated) |
| Methodology | Agile Scrum — 1-week sprints |
| Duration | 7 Weeks (Sprints 0–6) |
| Team Size | 5 persons: 1 PM, 1 BA, 2 Devs, 1 QA |
| Estimated Budget | INR 22–28 Lakhs |

# 1. Project Overview and Goals

DairyPro 360 is a modular dairy management system that will replace all paper-based and spreadsheet-driven operations of the client dairy business. The project will be delivered by a 5-person team over 7 weeks using Agile Scrum with 1-week sprints.

The system covers 6 functional domains: milk production, cattle health, inventory, sales & distribution, employee management, and financial reporting. The technology stack is Python/Django (backend), React.js + Tailwind CSS (frontend), and PostgreSQL (database).

| Goal | Success Criteria |
| --- | --- |
| Digital milk records | 100% of collections entered digitally from Day 1 of go-live |
| Cattle health traceability | All health events logged within 24 hours |
| Financial reporting | P&L and cash flow available on demand |
| System stability | Zero critical bugs at UAT sign-off |
| On-time delivery | Go-live in Week 7 as planned |

# 2. Work Breakdown Structure (WBS)

## Phase 0 — Project Initiation (Week 0)

- Sign off BRD v1.1 and kick off project

- Set up GitHub repository and CI/CD pipeline

- Provision dev, staging, and production environments

- Complete Solution Architecture (Agent 7 deliverable)

- Sprint 0 planning: backlog grooming, story point estimation

## Phase 1 — Foundation (Week 1)

- Database schema migration (all 18 tables)

- Authentication module: JWT login, RBAC, user management

- Cattle registry CRUD + tag management

- Basic React app scaffold with routing, Tailwind theme, sidebar

## Phase 2 — Core Production Modules (Week 2–3)

- Milk production entry per cow per session (morning/afternoon/evening)

- Quality and fat% capture with validation

- Cattle health records, vaccinations, vet visit logging

- Daily and monthly production summary reports

- Frontend: Dashboard KPIs, Milk Entry, Cattle Health screens

## Phase 3 — Inventory & Sales (Week 3–4)

- Inventory management: feed, medicine, equipment tracking

- Reorder alerts and supplier management

- Sales orders, customer management, and delivery tracking

- GST-compliant invoice auto-generation

- Frontend: Inventory, Sales Orders, Invoice screens

## Phase 4 — HR & Finance (Week 4–5)

- Employee records, attendance, and leave management

- Monthly payroll calculation (PF + ESI deductions) and payslip generation

- Double-entry accounts ledger

- P&L and cash flow report generation

- PDF and Excel export for all reports

- Frontend: HR Roster, Financial Reports screens with charts

## Phase 5 — Integration, Testing & Hardening (Week 5–6)

- End-to-end integration testing across all modules

- Security audit: SQL injection, XSS, auth bypass testing

- Performance testing under 500 concurrent user load

- Bug fix sprint (all critical and high bugs resolved)

- Data migration scripts for existing records

## Phase 6 — UAT & Go-Live (Week 7)

- User Acceptance Testing with Farm Manager, Accountant, and Vet

- UAT sign-off document

- 2-day user training programme

- Production deployment (Docker + cloud server)

- Hypercare period: 2 weeks of close support post go-live

# 3. Timeline with Milestones

| Week | Sprint | Key Deliverables | Milestone |
| --- | --- | --- | --- |
| Week 0 | Sprint 0 | BRD sign-off, architecture complete, environments ready | M-01: Project Kickoff |
| Week 1 | Sprint 1 | DB schema, Auth, Cattle registry, React scaffold | M-02: Foundation Live |
| Week 2 | Sprint 2 | Milk entry, quality capture, cattle health records | M-03: Core Ops Ready |
| Week 3 | Sprint 3 | Production summaries, inventory module, reorder alerts | M-04: Inventory Live |
| Week 4 | Sprint 4 | Sales orders, invoicing, supplier management | M-05: Sales Module Live |
| Week 5 | Sprint 5 | HR, payroll, finance ledger, P&L reports | M-06: Finance Module Live |
| Week 6 | Sprint 6 | Testing, security, bug fixes, data migration | M-07: Feature Freeze |
| Week 7 | Sprint 7 | UAT, training, production deployment | M-08: GO-LIVE |

# 4. Gantt Chart — Sprint Timeline

| Module / Activity | W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Architecture & Setup | ■ | ■ |  |  |  |  |  |  |
| Auth & User Management |  | ■ | ■ |  |  |  |  |  |
| Cattle Management |  | ■ | ■ | ■ |  |  |  |  |
| Milk Production |  |  | ■ | ■ |  |  |  |  |
| Inventory |  |  |  | ■ | ■ |  |  |  |
| Sales & Invoicing |  |  |  |  | ■ | ■ |  |  |
| HR & Payroll |  |  |  |  |  | ■ | ■ |  |
| Finance & Reports |  |  |  |  |  | ■ | ■ |  |
| QA, Testing & Bug Fix |  |  | ■ | ■ | ■ | ■ | ■ |  |
| UAT & Go-Live |  |  |  |  |  |  |  | ■ |

# 5. Resource Allocation

| Role | Person | W0 | W1 | W2 | W3 | W4 | W5 | W6 | W7 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Manager | PM Agent | 100% | 50% | 50% | 50% | 50% | 50% | 75% | 100% |
| Business Analyst | BA Agent | 100% | 75% | 50% | 25% | 25% | 25% | 50% | 100% |
| Backend Developer | Dev Agent 1 | 50% | 100% | 100% | 100% | 100% | 100% | 75% | 50% |
| Frontend Developer | Dev Agent 2 | 25% | 100% | 100% | 100% | 100% | 100% | 75% | 50% |
| Quality Analyst | QA Agent | 0% | 25% | 50% | 75% | 75% | 100% | 100% | 100% |

# 6. Risk Register with Mitigation Strategies

| Risk | Prob. | Impact | Exposure | Mitigation |
| --- | --- | --- | --- | --- |
| Scope creep | High | High | Critical | Strict change control; all scope changes require PM + sponsor approval in writing |
| User adoption resistance | High | High | Critical | Change management plan; 2-day training; change champions per department |
| Django/PostgreSQL performance issues at scale | Low | High | Medium | Load testing in Week 6; DB indexing strategy defined in architecture |
| Data migration errors | Medium | High | High | Pilot migration (10% of records); BA signs off on data quality |
| Key staff unavailability for UAT | Low | Medium | Medium | Schedule UAT 2 weeks ahead; identify backup testers |
| Internet outage at farm (field worker entry) | Medium | Medium | Medium | Paper backup procedure defined; PWA offline mode in Phase 2 roadmap |

# 7. Communication Plan

| Meeting / Report | Frequency | Participants | Format | Owner |
| --- | --- | --- | --- | --- |
| Daily Standup | Daily (15 min) | All agents + PM | Video call / async update | PM Agent |
| Sprint Planning | Every Monday | All agents | 2-hour planning session | PM Agent |
| Sprint Review | Every Friday | All agents + Sponsor | Demo + retrospective | PM Agent |
| Stakeholder Status Report | Weekly | Sponsor, Farm Manager | Email summary + task board link | PM Agent |
| UAT Session | Week 7 (2 days) | Farm Mgr, Accountant, Vet | In-person / remote walkthrough | BA Agent |
| Go/No-Go Decision | End of Week 6 | PM, Sponsor, QA | Meeting with checklist sign-off | PM Agent |

# 8. Definition of Done (DoD) — Per Phase

## DoD — Each Sprint

- All user stories in the sprint backlog are implemented and pass unit tests

- No Critical or High severity bugs remain open

- Code is reviewed and merged to main branch

- Staging environment is updated and smoke-tested

- Sprint demo delivered and stakeholder sign-off obtained

## DoD — Feature Freeze (Week 6)

- All 6 functional modules implemented and integrated

- API documentation complete and accurate

- All test cases executed; pass rate >= 90%

- Zero Critical bugs; Zero High bugs

- Performance test confirms < 2s dashboard load for 500 concurrent users

- Security audit passed (no SQL injection, XSS, or auth bypass vulnerabilities)

## DoD — Go-Live (Week 7)

- UAT completed and signed off by Farm Manager, Accountant, and Vet

- Production environment deployed and stable

- User training completed (minimum 80% staff attendance)

- Data migration validated by BA Agent

- Hypercare support plan in place for 2 weeks post go-live

# 9. Budget Estimate

| Category | Estimated Cost (INR) |
| --- | --- |
| Backend Development (7 weeks) | 7,00,000 |
| Frontend Development (7 weeks) | 6,00,000 |
| QA & Testing | 3,00,000 |
| Project Management & BA | 3,50,000 |
| Cloud Infrastructure (1 year) | 1,50,000 |
| Third-party Services (SMS, Email) | 50,000 |
| Contingency (10%) | 2,15,000 |
| TOTAL ESTIMATED | 23,65,000 |

Project Plan prepared by PM Agent  |  DairyPro 360  |  25 May 2026  |  v1.0